## Vendors
HIRING VENDORS
|  | Can give to 1 Contractor or 5 Vendors | [6 empty] | Can give to 1 or 2 vendors |  | Can give to 1 or more vendors
DESIGN COMPONENTS |  | Deomolition, Brickwork, plaster, PCC | Electrical | Plumbing | HVAC | POP / Gypsum | Paint | Marble / Tile fixing | Panelling (Wall / ceiling) | Carpentry @ site | Furniture, Vanities
Floor plan | Marble, Tile, Wooden | X |  | X | X |  | X | X |  |  | X
Wall elevations | Marble, Panelling, texture paint, wallpaper, other | X | X |  | X |  | X | X | X
Ceiling plan | Coves, panelling, lights, fans, AC | X | X |  | X | X | X |  | X
Automation | Lights, Curtains, drawings |  | X
Entertainment | TV, Music, Wi Fi, CCTV |  | X
Sanitaryware | Digital, manual, ceiling / floor / wall, other |  | X
Kitchen | Marble, Tiles, light points, drains, appliances | X | X | X |  |  |  | X
Bathroom | Marble, Tile, drains, light points, levels, Glass, other |  | X | X |  |  |  | X
Wardrobes | Heights, light points |  | X
Doors | Internal / trap |  | X | [6 empty] | X
Storages | Shoe / other | [8 empty] | X
Apart from above, there is Glass, Metal, and maybe few other categories for which we'd hire specialist vendors.

## Projects
URGENCY | PROJECTS | SELECTION | DWGs | 3D | SAMPLE | SPECS | VENDOR | PI | PAYMENT | DELIVERY | EXECUTION | NOTES | DAYS | START | END
| Floor planning | N/A | Done | N/A
| Design & Concept | N/A | WIP | WIP | [10 empty] | 0
| Sanitaryware | WIP | Done | [11 empty] | 0
| Lights - Architectural | WIP | Done | N/A | [8 empty] | 5 |  | 1900-01-04
| Lights - Decorative | Pending | Done | N/A | [10 empty] | 0
| Kitchen | Pending | Done | [9 empty] | 10 | 2023-07-14 | 1900-01-23
| HVAC | N/A | Done | N/A | [8 empty] | 10 |  | 1900-01-09
| Waterproofiing | N/A | N/A | N/A
| Plumbing (internal) | N/A | N/A | N/A | [8 empty] | 5 | 2023-07-10 | 2023-07-15
| Fire / Smoke | N/A | N/A | N/A
| Mobile Booster | N/A | ?? | N/A | [8 empty] | 3 | 2023-07-10 | 2023-07-13
| Wi Fi / CCTV | Pending | ?? | N/A | [10 empty] | 0
| Home Automation | Pending | Pending | N/A | [10 empty] | 0
| Wiring (internal) | N/A | N/A | N/A | [8 empty] | 10 | 2023-07-10 | 2023-07-20
| Marble - Mat | WIP | N/A | N/A | [10 empty] | 0
| Tiles - commercial (mat) | N/A | Pending | N/A
| Tiles - Vitrified (mat) | Pending | Pending | N/A
| Marble & Tile (install) | N/A | N/A | N/A
| Marble - polish | N/A | N/A | N/A | [8 empty] | 8 |  | 1900-01-07
| POP | N/A | WIP | N/A | [10 empty] | 0
| Carpentry works | N/A | Pending | [9 empty] | 4 |  | 1900-01-03
| Paint - plain v/s textured | Pending | Pending | [11 empty] | 0
| Wallpaper | Pending | Pending | [11 empty] | 0
| Wall paneling | Pending | Pending | [11 empty] | 0
| TV Units | Pending | Pending | [11 empty] | 0
| Metal works | Pending | Pending | [9 empty] | 6 |  | 1900-01-05
| Wardrobes | Pending | Pending | [9 empty] | 10 | 2023-07-12 | 1900-01-21
| Switch sockets | Pending | Pending | [11 empty] | 0
| Vanities | Pending | Pending | [11 empty] | 0
| Doors - internal | Pending | Pending | [9 empty] | 40 |  | 1900-02-08
| Doors - Main | N/A | N/A | N/A | [10 empty] | 0
| Shower Cubicles | Pending | Pending | [11 empty] | 0
| Curtains / Blinds | Pending | Pending | [11 empty] | 0
| Furniture | Pending | Pending | [11 empty] | 0
0
Formulas:
END = Table2[[#This Row],[DAYS]]+Table2[[#This Row],[START]]

## Sheet1
CATEGORY | ZONE | LOCATION | TYPE | ACTIVITY | LINK | DAYS (P) | DAYS (R) | S.DATE | E.DATE | FOCUS | STATUS | NOTES | VENDOR | OWNER
Design | BM |  |  | Civil plan (Walls)
Design | GF |  |  | Flooring plan
Design | FF |  |  | Furniture plan
Design | SF |  |  | Plumbing DWG
Design | Façade |  |  | Wall electrical DWG.
Design | Front Yrd | Master Bed.R | Design | Light & Fan DWG.
Design | Back Yrd |  | Purchase | HVAC DWG.
Design |  |  | Supervisor | False ceiling DWG.
Design |  | Living & Dining | Supervisor | Concept / 3D
Design |  | Master Bed.R | Supervisor | Concept / 3D
Design |  | Medha Bed.R |  | Concept / 3D
Design |  | Jaiditya Bed.R |  | Concept / 3D
Design |  | Parents Bed.R |  | Concept / 3D
Design |  | Master Bath |  | Concept / 3D
Design |  | Medha Bath |  | Concept / 3D
Design |  | Jaiditya Bath |  | Concept / 3D
Design |  | Parents Bath |  | Concept / 3D
Design |  | Bath Master |  | Elevations
Design |  | Medha Bath |  | Elevations
Design |  | Living & Dining |  | Elevations
Design |  | Dining |  | Elevations
Design |  | Lobby Wall |  | Elevations
Design |  | Medha Bed.R |  | TV Wall
Design |  | Medha Bed.R |  | Bed back wall
Design |  | Medha Bed.R |  | TV Wall
Design |  | Medha Bed.R |  | Bed back wall
Design |  | Parents Bed.R |  | TV Wall
Design |  | Parents Bed.R |  | Bed back wall
Design |  | Jaiditya Bed.R |  | TV Wall
Design |  | Jaiditya Bed.R |  | Bed back wall
Civil |  |  |  | Autocad DWG
Civil |  |  |  | Quotes
Civil |  |  |  | Vendor Contract
Civil |  |  |  | Payment 1
Civil |  |  |  | DLF Induction
Civil |  |  |  | Demolition
Civil |  |  |  | Malba removal
Civil |  |  |  | Payment 2
Civil |  |  |  | Block Wall
Civil |  |  |  | Payment 3
Civil |  |  |  | Plaster
Civil |  |  |  | PCC
Civil |  |  |  | Payment FINAL
Plumbing |  |  |  | Quotes
Plumbing |  |  |  | Vendor Contract
Plumbing |  |  |  | Payment 1
Plumbing |  |  |  | DLF Induction
Plumbing |  |  |  | Sewage piping
Plumbing |  |  |  | Inlet piping
Plumbing |  |  |  | Payment 2
Plumbing |  |  |  | Concealed parts
Plumbing |  |  |  | Pressure testing
Plumbing |  |  |  | Payment 3
Plumbing |  |  |  | Sanitaryware/ CP fittings
Plumbing |  |  |  | Payment FINAL
Waterproofing |  |  |  | Quotes
Waterproofing |  |  |  | Vendor Contract
Waterproofing |  |  |  | Payment 1
Waterproofing |  |  |  | DLF Induction
Waterproofing |  |  |  | Base and final coats
Waterproofing |  |  |  | Water testing
Waterproofing |  |  |  | Payment FINAL
Lights - Architectural |  |  |  | Brand
Lights - Architectural |  |  |  | Quotes
Lights - Architectural |  |  |  | Vendor Contract
Lights - Architectural |  |  |  | Autocad DWG
Lights - Architectural |  |  |  | Payment 1
Lights - Architectural |  |  |  | Technical DWG
Lights - Architectural |  |  |  | Payment FINAL
Lights - Architectural |  |  |  | Material delivery
Lights - Decorative |  |  |  | Brand
Lights - Decorative |  |  |  | Selection
Lights - Decorative |  |  |  | Quotes
Lights - Decorative |  |  |  | Vendor Contract
Lights - Decorative |  |  |  | Payment 1
Lights - Decorative |  |  |  | Technical DWG
Lights - Decorative |  |  |  | Payment FINAL
Lights - Decorative |  |  |  | Material delivery
Home automation |  |  |  | Quotes
Home automation |  |  |  | Vendor Contract
Home automation |  |  |  | Payment 1
Home automation |  |  |  | Technical DWG
Home automation |  |  |  | Material delivery
Home automation |  |  |  | Payment 2
Home automation |  |  |  | Face plates
Home automation |  |  |  | Panel dressing
Home automation |  |  |  | commissioning
Home automation |  |  |  | Payment FINAL
Electrical |  |  |  | Quotes
Electrical |  |  |  | Vendor Contract
Electrical |  |  |  | Payment 1
Electrical |  |  |  | DLF Induction
Electrical |  |  |  | Ceiling Conduting
Electrical |  |  |  | Wall, Floor Conduting
Electrical |  |  |  | GI boxes fixing
Electrical |  |  |  | Payment 2
Electrical |  |  |  | Wiring + Cable work
Electrical |  |  |  | Payment 3
Electrical |  |  |  | DB fixing and dressing
Electrical |  |  |  | Lights and plates fixing
Electrical |  |  |  | Payment 4
Electrical |  |  |  | Decorative light installation
Electrical |  |  |  | Payment FINAL
Sanitaryware |  | Master Bath |  | Brand
Sanitaryware |  | Master Bath |  | Quotes
Sanitaryware |  | Master Bath |  | Vendor Contract
Sanitaryware |  | Master Bath |  | Cistern-WC
Sanitaryware |  | Master Bath |  | Basin
Sanitaryware |  | Master Bath |  | Mixer
Sanitaryware |  | Master Bath |  | Shower system
Sanitaryware |  | Master Bath |  | Steam
Sanitaryware |  | Master Bath |  | Drains
Sanitaryware |  | Master Bath |  | Accessories
Sanitaryware |  | Master Bath |  | Payment FINAL
Sanitaryware |  | Master Bath |  | Delivery
Sanitaryware |  | Medha Bath |  | Brand
Sanitaryware |  | Medha Bath |  | Vendor Quotes
Sanitaryware |  | Medha Bath |  | Vendor Contract
Sanitaryware |  | Medha Bath |  | Cistern-WC
Sanitaryware |  | Medha Bath |  | Basin
Sanitaryware |  | Medha Bath |  | Mixer
Sanitaryware |  | Medha Bath |  | Shower system
Sanitaryware |  | Medha Bath |  | Steam
Sanitaryware |  | Medha Bath |  | Drains
Sanitaryware |  | Medha Bath |  | Accessories
Sanitaryware |  | Medha Bath |  | Payment FINAL
Sanitaryware |  | Medha Bath |  | Delivery
HVAC |  |  |  | Autocad DWG
HVAC |  |  |  | Vendor Quotes
HVAC |  |  |  | Vendor Contract
HVAC |  |  |  | Payment 1
HVAC |  |  |  | DLF Induction
HVAC |  |  |  | Technical DWG
HVAC |  |  |  | CU piping + wiring
HVAC |  |  |  | Pressure testing
HVAC |  |  |  | Payment 2
HVAC |  |  |  | Ducting
HVAC |  |  |  | Collar work
HVAC |  |  |  | Payment 3
HVAC |  |  |  | IDU & ODU installation
HVAC |  |  |  | Grill fixing
HVAC |  |  |  | commissioning
HVAC |  |  |  | Payment FINAL
Smoke |  |  |  | Autocad DWG
Smoke |  |  |  | Vendor Quotes
Smoke |  |  |  | Vendor Contract
Smoke |  |  |  | Payment 1
Smoke |  |  |  | DLF Induction
Smoke |  |  |  | Headers
Smoke |  |  |  | Payment 2
Smoke |  |  |  | Branches
Smoke |  |  |  | Pressure testing
Smoke |  |  |  | Payment 3
Smoke |  |  |  | Flexible pipe
Smoke |  |  |  | Alignment
Smoke |  |  |  | Sprinkler head cap
Smoke |  |  |  | Payment FINAL
Fire safety |  |  |  | Autocad DWG
Fire safety |  |  |  | Vendor Quotes
Fire safety |  |  |  | Vendor Contract
Fire safety |  |  |  | Payment 1
Fire safety |  |  |  | DLF Induction
Fire safety |  |  |  | Ceiling Conduting
Fire safety |  |  |  | Wiring
Fire safety |  |  |  | Detector fixing
Fire safety |  |  |  | Payment FINAL
POP |  |  |  | Autocad DWG
POP |  |  |  | Vendor Quotes
POP |  |  |  | Vendor Contract
POP |  |  |  | Payment 1
POP |  |  |  | DLF Induction
POP |  |  |  | wall bullpads
POP |  |  |  | Wall punning
POP |  |  |  | Payment 2
POP |  |  |  | Ceiling frame+ wire mesh
POP |  |  |  | Payment 3
POP |  |  |  | Ceiling plaster
POP |  |  |  | coves
POP |  |  |  | Ceiling Grooves
POP |  |  |  | Payment 4
POP |  |  |  | Moulding
POP |  |  |  | Light cutting
POP |  |  |  | Grill cutting
POP |  |  |  | Repairing if needed
POP |  |  |  | Payment FINAL
Vitrified Tiles |  |  |  | Selection
Vitrified Tiles |  |  |  | Vendor Quotes
Vitrified Tiles |  |  |  | Payment FINAL
Vitrified Tiles |  |  |  | Delivery
Vitrified Tiles |  |  |  | Autocad DWG
Vitrified Tiles |  |  |  | Vendor Contract
Vitrified Tiles |  |  |  | DLF Induction
Vitrified Tiles |  |  |  | Fixing
Vitrified Tiles |  |  |  | Payment 2
Vitrified Tiles |  |  |  | Grouting+Cleaning
Vitrified Tiles |  |  |  | Payment FINAL
Commercial Tiles |  |  |  | Selection
Commercial Tiles |  |  |  | Vendor Quotes
Commercial Tiles |  |  |  | Payment FINAL
Commercial Tiles |  |  |  | Delivery
Commercial Tiles |  |  |  | Vendor Contract
Commercial Tiles |  |  |  | Payment 1
Commercial Tiles |  |  |  | DLF Induction
Commercial Tiles |  |  |  | Fixing
Commercial Tiles |  |  |  | Payment 2
Commercial Tiles |  |  |  | Grouting+Cleaning
Commercial Tiles |  |  |  | Payment FINAL
Marble |  |  |  | Selection
Marble |  |  |  | Vendor Quotes
Marble |  |  |  | Payment FINAL
Marble |  |  |  | Delivery
Marble |  |  |  | Autocad DWG
Marble |  |  |  | Vendor Quotes
Marble |  |  |  | Vendor Contract
Marble |  |  |  | Payment 1
Marble |  |  |  | DLF Induction
Marble |  |  |  | Chemical screeding
Marble |  |  |  | Marble laying
Marble |  |  |  | Payment 2
Marble |  |  |  | Skirting
Marble |  |  |  | Counter fixing
Marble |  |  |  | Payment 3
Marble |  |  |  | Metal/Marble inlay
Marble |  |  |  | Marble grinding
Marble |  |  |  | polishing work
Marble |  |  |  | Payment 4
Marble |  |  |  | Final polish
Marble |  |  |  | Payment FINAL
Mod. Kitchen |  |  |  | Brand
Mod. Kitchen |  |  |  | Vendor Quotes
Mod. Kitchen |  |  |  | Vendor Contract
Mod. Kitchen |  |  |  | Payment 1
Mod. Kitchen |  |  |  | Measurement
Mod. Kitchen |  |  |  | Mat. selection
Mod. Kitchen |  |  |  | Technical DWG
Mod. Kitchen |  |  |  | Payment FINAL
Mod. Kitchen |  |  |  | Delivery
Mod. Kitchen |  |  |  | DLF Induction
Mod. Kitchen |  |  |  | Carcuss fixing
Mod. Kitchen |  |  |  | Shutters/Accessories fixing
Carpentry |  |  |  | Autocad DWG
Carpentry |  |  |  | Quotes
Carpentry |  |  |  | Vendor Contract
Carpentry |  |  |  | Payment 1
Carpentry |  |  |  | Delivery
Carpentry |  |  |  | Alu.Frame
Carpentry |  |  |  | Trapdoor
Carpentry |  |  |  | Payment 2
Carpentry |  |  |  | Base work for wall panelling
Carpentry |  |  |  | Staircase basework
Carpentry |  |  |  | Wood pressing
Carpentry |  |  |  | Veneer/Hdf pressing
Carpentry |  |  |  | Payment 3
Carpentry |  |  |  | Moulding
Carpentry |  |  |  | Partitions for slider
Carpentry |  |  |  | Servant wardrobe
Carpentry |  |  |  | Payment FINAL
MS work |  |  |  | Technical DWG
MS work |  |  |  | Vendor Quotes
MS work |  |  |  | Vendor Contract
MS work |  |  |  | Payment 1
MS work |  |  |  | DLF Induction
MS work |  |  |  | Technical DWG
MS work |  |  |  | Bulk head
MS work |  |  |  | Floating counter frame
MS work |  |  |  | Staircase Structure
MS work |  |  |  | Red oxide
MS work |  |  |  | Payment FINAL
Panelling - Wooden |  |  |  | Brand
Panelling - Wooden |  |  |  | Vendor Quotes
Panelling - Wooden |  |  |  | Vendor Contract
Panelling - Wooden |  |  |  | Payment 1
Panelling - Wooden |  |  |  | Measurement
Panelling - Wooden |  |  |  | Mat. selection
Panelling - Wooden |  |  |  | Technical DWG
Panelling - Wooden |  |  |  | Payment FINAL
Panelling - Wooden |  |  |  | Delivery
Panelling - Wooden |  |  |  | Fixing
Panelling - Marble |  |  |  | Selection
Panelling - Marble |  |  |  | Vendor Quotes
Panelling - Marble |  |  |  | Payment FINAL
Panelling - Marble |  |  |  | Delivery
Panelling - Marble |  |  |  | Fixing
Panelling - Marble |  |  |  | Final polish
Panelling - Metal |  |  |  | Selection
Panelling - Metal |  |  |  | Vendor Quotes
Panelling - Metal |  |  |  | Payment FINAL
Panelling - Metal |  |  |  | Delivery
Panelling - Metal |  |  |  | Fixing
Mod. Wardrobe |  |  |  | Brand
Mod. Wardrobe |  |  |  | Vendor Quotes
Mod. Wardrobe |  |  |  | Vendor Contract
Mod. Wardrobe |  |  |  | Payment 1
Mod. Wardrobe |  |  |  | Measurement
Mod. Wardrobe |  |  |  | Mat. selection
Mod. Wardrobe |  |  |  | Technical DWG
Mod. Wardrobe |  |  |  | Payment FINAL
Mod. Wardrobe |  |  |  | Delivery
Mod. Wardrobe |  |  |  | Carcuss fixing
Mod. Wardrobe |  |  |  | Shutters/Accessories fixing
Internal doors |  |  |  | Brand
Internal doors |  |  |  | Vendor Quotes
Internal doors |  |  |  | Vendor Contract
Internal doors |  |  |  | Payment 1
Internal doors |  |  |  | Measurement
Internal doors |  |  |  | Mat. selection
Internal doors |  |  |  | Technical DWG
Internal doors |  |  |  | Payment FINAL
Internal doors |  |  |  | Rough ground fixing
Internal doors |  |  |  | Delivery
Internal doors |  |  |  | Door frame installation
Internal doors |  |  |  | Door installation
Internal doors |  |  |  | Accessories
Internal doors |  |  |  | Architrave
Main door |  |  |  | Brand
Main door |  |  |  | Vendor Quotes
Main door |  |  |  | Vendor Contract
Main door |  |  |  | Payment 1
Main door |  |  |  | Measurement
Main door |  |  |  | Mat. selection
Main door |  |  |  | Technical DWG
Main door |  |  |  | Payment FINAL
Main door |  |  |  | Rough ground fixing
Main door |  |  |  | Delivery
Main door |  |  |  | Door frame installation
Main door |  |  |  | Door installation
Main door |  |  |  | Accessories
Main door |  |  |  | Architrave
Cubicles |  |  |  | Brand
Cubicles |  |  |  | Selection
Cubicles |  |  |  | Autocad DWG
Cubicles |  |  |  | Quotes
Cubicles |  |  |  | Vendor Contract
Cubicles |  |  |  | Payment 1
Cubicles |  |  |  | Measurement
Cubicles |  |  |  | Technical DWG
Cubicles |  |  |  | Delivery
Cubicles |  |  |  | Payment FINAL
Cubicles |  |  |  | Installation
Cubicles |  |  |  | Accessories
Mirrors |  |  |  | Brand
Mirrors |  |  |  | Selection
Mirrors |  |  |  | Quotes
Mirrors |  |  |  | Vendor Contract
Mirrors |  |  |  | Payment 1
Mirrors |  |  |  | Measurement
Mirrors |  |  |  | Technical DWG
Mirrors |  |  |  | Delivery
Mirrors |  |  |  | Payment FINAL
Mirrors |  |  |  | Installation
Vanities |  |  |  | Brand
Vanities |  |  |  | Vendor Quotes
Vanities |  |  |  | Vendor Contract
Vanities |  |  |  | Payment 1
Vanities |  |  |  | Measurement
Vanities |  |  |  | Mat. selection
Vanities |  |  |  | Technical DWG
Vanities |  |  |  | Payment FINAL
Vanities |  |  |  | Delivery
Vanities |  |  |  | Carcuss fixing
Vanities |  |  |  | Shutters/Accessories fixing
Furniture |  |  |  | Brand
Curtains |  |  |  | Selection
Curtains |  |  |  | Vendor Quotes
Curtains |  |  |  | Vendor Contract
Curtains |  |  |  | Payment 1
Curtains |  |  |  | Delivery
Curtains |  |  |  | Payment FINAL
Curtains |  |  |  | Installation
Art |  |  |  | Brand
Art |  |  |  | Selection
Art |  |  |  | Vendor Quotes
Art |  |  |  | Vendor Contract
Art |  |  |  | Payment FINAL
Art |  |  |  | Delivery
Art |  |  |  | Installation
Wooden flooring |  |  |  | Brand
Wooden flooring |  |  |  | Selection
Wooden flooring |  |  |  | Vendor Quotes
Wooden flooring |  |  |  | Vendor Contract
Wooden flooring |  |  |  | Payment FINAL
Wooden flooring |  |  |  | Delivery
Wooden flooring |  |  |  | Installation
Plain Paint |  |  |  | Autocad DWG
Plain Paint |  |  |  | Quotes
Plain Paint |  |  |  | Vendor Contract
Plain Paint |  |  |  | Payment 1
Plain Paint |  |  |  | DLF Induction
Plain Paint |  |  |  | Selection
Plain Paint |  |  |  | Base work
Plain Paint |  |  |  | Payment 2
Plain Paint |  |  |  | Coats
Plain Paint |  |  |  | Final coat
Plain Paint |  |  |  | Payment FINAL
Textured Paint |  |  |  | Autocad DWG
Textured Paint |  |  |  | Quotes
Textured Paint |  |  |  | Vendor Contract
Textured Paint |  |  |  | Payment 1
Textured Paint |  |  |  | DLF Induction
Textured Paint |  |  |  | Selection
Textured Paint |  |  |  | Base work
Textured Paint |  |  |  | Payment 2
Textured Paint |  |  |  | Coats
Textured Paint |  |  |  | Final coat
Textured Paint |  |  |  | Payment FINAL
Micro-concrete |  |  |  | Quotes
Micro-concrete |  |  |  | Vendor Contract
Micro-concrete |  |  |  | Payment 1
Micro-concrete |  |  |  | DLF Induction
Micro-concrete |  |  |  | Selection
Micro-concrete |  |  |  | Base work
Micro-concrete |  |  |  | Payment 2
Micro-concrete |  |  |  | Coats
Micro-concrete |  |  |  | Final coat
Micro-concrete |  |  |  | Payment FINAL
Polish/PU |  |  |  | Autocad DWG
Polish/PU |  |  |  | Quotes
Polish/PU |  |  |  | Vendor Contract
Polish/PU |  |  |  | Payment 1
Polish/PU |  |  |  | DLF Induction
Polish/PU |  |  |  | Selection
Polish/PU |  |  |  | Base work
Polish/PU |  |  |  | Payment 2
Polish/PU |  |  |  | Coats
Polish/PU |  |  |  | Final coat